## Slide 1
Finance GenAI Document Studio
Feb–Dec 2026 | Phase 1: 6 Devs (£352k) | Phase 2: 2 Devs (£117k) | Total: £469,860 | MVP: 31 Jul | Full Product: 31 Dec
PHASE 1: MVP DEVELOPMENT (FEB - JUL 2026) | £352,395 (6 Developers) | Launch: 31 Jul 2026
FEB
MAR
APR
MAY
JUN
JUL
Foundation
Core Authoring
Data Prep + Viz
AI Narration
Governance
MVP Launch
• AWS infra setup • SSO/Auth • CSV→Parquet pipeline • Schema validation • CI/CD + security baseline • Backlog + sample data • End-to-End: Infra → Ingest
• Block editor + params • Live preview • Core blocks (title/table/chart) • Themes/branding/blueprint • Versioning • End-to-End: Author → Preview
• Visual data-prep canvas • DuckDB preview • Advanced tables/charts
• Export functionality • Profiling/drift alerts • End-to-End: Prep → Visualize
• Bedrock + RAG • Narration prompts/JSON/critique • Source highlighting/tracability • Redaction/policy • End-to-End: Grounded narration
• RBAC/ABAC workflows • Review/approval + collaboration + commentary + sign-off + watermarks • Provenance + logs • Security hardening/ Compliance • End-to-End: Governed run
• Scheduling + notifications • Observability dashboards/Cloudwatch • Full E2E/testing/UAT • MVP Go-Live (31 Jul) • Training/handover
✓ Infra
✓ Authoring
✓ Data-viz
✓ AI ready
✓ Governed
✓ MVP Live
PHASE 2: ADVANCED PRODUCT (AUG - DEC 2026) | £117,465 (2 Developers: Dev1 + Dev4) | Launch: 31 Dec 2026
AUG
SEP
OCT
NOV
DEC
Scenario + MCP
• Scenario Studio (macro packs) • Model Context Protocol (MCP) integration basics • Grounded Compare/Explain delta + drivers • Change-aware templates • Snippets library + search
Advanced AI
• Full MCP implementation (secure tool calling, external APIs/databases) • Advanced agentic flows (multi-pass, CoT, tool orchestration) • Hybrid RAG + re-ranking • Advanced data contracts/auto-fixes • Cost guardrails + command palette
Plugins + Collab
• Plugin SDK (custom blocks/validators) • Real-time co-editing (y-js) • Custom chart gallery • Golden-run testing + CI regression • Ops guardrails (token ceilings, queues)
Integrations
• MCP-powered integrations (AWS tools, BI embeds) • Teams distribution • Accessibility (WCAG AA+) + i18n • Zero-copy + performance scaling • Advanced lineage
Full Launch
• Full-scale load/security testing • Visual regression suite • Production stabilization • Feedback polish • Full Product Launch (31 Dec)
✓ MCP basics
✓ AI/Gov
✓ Plugins
✓ Complete
✓ V1.0 Live
Barclays Finance GenAI Innovation Lab | 11-Month Plan (Feb-Dec 2026) | Budget: £469,860 + AWS/Bedrock £30-50k | Model Context Protocol (MCP) for secure tool calling & agentic flows
Enterprise-grade, AI-powered Document Studio for Barclays Finance to automate publication-grade reports (PDF/DOCX/HTML) from large CSV/Parquet datasets. Enables business users to build reusable, parameterized templates with visual data prep, rich tables/charts, grounded AI narratives (Bedrock Claude Sonnet + Titan embeddings), live previews, review/approval workflows, colleague collaboration, full provenance, lineage, and auditability. Targets 70–80% reduction in manual effort for MI/regulatory reporting with strong governance, compliance, and explainability.
Category | Details
Business Benefits | 70–80% reduction in manual effort for MI/regulatory reporting Standardized, consistent outputs across Finance Faster report cycles (daily/quarterly automation) Enhanced accuracy & compliance via grounding + human approval Explainable AI with full provenance for auditors Self-service for business users (no IT dependency) Cost control through token guardrails
Success Metrics | MVP live: 31 Jul 2026 Full Product live: 31 Dec 2026 Preview latency: p95 <1.2s First-pass QA acceptance: ≥90% Narrative factual accuracy: ≥97% Manual effort reduction: 80%+ User adoption: 100+ templates & active users by Dec Run success rate: ≥99% Cost per document: Within target (via dashboards) Cache hit rate: ≥60%
Category | Details
Assumptions | Data sets identified and available AWS/Bedrock access SMEs available throughout No major scope changes; monthly steering reviews Reduced Phase 2 team sufficient for targeted enhancements
Risks | Timeline Slip MCP Integration Complexity Phase 2 Bandwidth Advanced AI/Security Issues Cost Overruns (tokens/cloud)
Tech Arch
Next.js (React), Blueprint + Tailwind, AG Grid, Recharts/ECharts, React Query FastAPI (Python) or NestJS Services, IAM, BAM GitLab pipeline, EKS, Lambda; SQS; Step Functions S3 (raw CSV, Parquet, outputs), DynamoDB/Postgres (metadata), ElastiCache/Redis DuckDB/Arrow, Athena S3 Vectors or pgvector on Aurora/Postgres AWS Bedrock, Claude Sonnet 4.5, Titan embeddings CSM, Secrets Manager, CloudWatch
Cost Item | Amount (£)
Phase 1 Team (6 devs, 6 months) | 352,395
Phase 2 Team (2 devs, 5 months) | 117,465
Total Team | 469,860

## Slide 2
Layer | Components | Details / Purpose
Frontend | Next.js (React), shadcn/ui + Tailwind, AG Grid, Recharts/ECharts, TipTap, React Query, Redux Toolkit (editor), optional y-js (later for co-editing) | Modern, responsive UI: three-pane builder, live preview, drag-drop blocks, theming (Barclays branding, dark/light). Fast state management and querying.
APIs | FastAPI (Python) or NestJS Services: Template, Data-Prep, Preview, Narration, Render, Runs, References, AuthZ | Microservices architecture: modular, scalable endpoints for all operations (e.g., narration calls Bedrock securely).
Compute | EKS for services; Lambda for burst jobs; SQS for work queues; Step Functions for long-running generations | Horizontal scaling; async processing for previews/runs; orchestration for multi-step workflows (data → narration → render).
Storage | S3 (raw CSV, Parquet, outputs, manifests) DynamoDB/Postgres (metadata) ElastiCache/Redis (cache) | Durable, versioned storage; fast metadata access; aggressive caching for previews (template + params + data hash).
Analytics | DuckDB/Arrow (preview & many full runs) Athena (very large scans) | Zero-copy, fast execution on Parquet; fallback for massive datasets.
Vectors | S3 Vectors or pgvector on Aurora/Postgres; Titan embeddings | Efficient RAG grounding over approved corpus; scalable retrieval.
Identity/Security | Cognito or enterprise OIDC/SAML; KMS; Secrets Manager; CloudFront + WAF | SSO, RBAC/ABAC, encryption at rest/transit, DDoS protection, column masking.
Observability | CloudWatch, OpenTelemetry traces, Sentry; cost dashboards | Metrics (latency/tokens/cache), traces, error tracking; admin visibility into usage/costs.
Technical Architecture (High-Level, AWS-Aligned)

## Slide 3
Category | Item | Details / Mitigation
Assumptions | AWS/Bedrock access (incl. MCP support) from 01 Feb 2026 | Pre-approved accounts; early prototyping if delayed.
 | Sample datasets/corpus available mid-Feb | Business provides early for testing/AI grounding.
 | SMEs available 4–8 hrs/week throughout (increased for Phase 2 MCP) | For prompt validation, UAT, and feedback.
 | No major scope changes; monthly steering reviews | Gated via MoSCoW and change control.
 | Reduced Phase 2 team sufficient for targeted enhancements | MVP stability allows focused work; contingency for +1 dev.
Risks | Timeline Slip | Mitigation: Monthly milestones + Dec buffer; early MVP de-risks Phase 2.
 | MCP Integration Complexity | Mitigation: Prototype in Phase 1; leverage AWS Bedrock MCP servers/best practices.
 | Phase 2 Bandwidth | Mitigation: High-priority features only; contingency +1 dev if needed.
 | Advanced AI/Security Issues | Mitigation: Iterative testing; strict MCP security (tool approval/logging).
 | Cost Overruns (tokens/cloud) | Mitigation: Enhanced guardrails/dashboards; reduced team in Phase 2.
Assumptions & Risks

## Slide 4
Business Benefits & Success Metrics
Category | Details | Target / KPI Details
Business Benefits | 70–80% reduction in manual effort for MI/regulatory reporting Standardized, consistent outputs across Finance Faster report cycles (daily/quarterly automation) Enhanced accuracy & compliance via grounding + human approval Explainable AI with full provenance for auditors Self-service for business users (no IT dependency) Cost control through token guardrails | Aligns with Barclays Standards/Blueprint and Document Generation tracks. Shifts from manual CSV → Word/PDF to parameterized, AI-assisted document studio. Enables scenario/stress testing and variance explanations.
Success Metrics | MVP live: 31 Jul 2026 Full Product live: 31 Dec 2026 Preview latency: p95 <1.2s First-pass QA acceptance: ≥90% Narrative factual accuracy: ≥97% Manual effort reduction: 80%+ User adoption: 100+ templates & active users by Dec Run success rate: ≥99% Cost per document: Within target (via dashboards) Cache hit rate: ≥60% | Measured via authoring time (≤2 days to first template), grounding coverage ≥95%, defects <0.5%, and post-launch surveys.

## Slide 5
Aspect | Details | Breakdown / Notes
Phase 1 (MVP: Feb–Jul 2026) | 6 Full-Time Developers Total Cost: £352,395 (6 months, salaries only) | Full team for rapid MVP delivery of all Must-Haves. Focus on core features, governance, and launch.
Dev1 (Lead/Arch/AI) | Annual: £211,000 6-Mo Cost: £105,500 | Leads architecture, AI integration (Bedrock/RAG), and overall technical direction.
Dev2 (Backend/API) | Annual: £152,216 6-Mo Cost: £76,108 | Handles FastAPI services, orchestration (Step Functions/SQS), and data pipelines.
Dev3 (Infra/Sec) | Annual: £17,646 6-Mo Cost: £8,823 | Manages AWS infra, security (KMS/WAF), CI/CD, and compliance hardening.
Dev4 (Frontend) | Annual: £119,112 6-Mo Cost: £59,556 | Builds Next.js UI, block editor, three-pane layout, and live preview.
Dev5 (UI/UX/Viz) | Annual: £95,395 6-Mo Cost: £47,698 | Focuses on shadcn/Tailwind theming, charts/tables (ECharts), and accessibility.
Dev6 (Data/Perf/RAG) | Annual: £109,420 6-Mo Cost: £54,710 | Handles DuckDB previews, Parquet pipelines, performance tuning, and Titan vectors.
Phase 2 (Advanced: Aug–Dec 2026) | 2 Developers (reduced team) Total Cost: £117,465 (5 months) | Focused enhancements (MCP, agentics, plugins); leverages MVP stability.
Dev1 (Lead/Advanced AI/MCP) | Annual: £211,000 Monthly: £17,583 5-Mo Cost: £87,915 | Leads Phase 2 AI advancements, MCP integration, and agentic flows.
Dev4 (Frontend/Plugins) | Annual: £119,112 Monthly: £9,926 5-Mo Cost: £29,550 | Handles UI extensions (plugins, co-editing, command palette).
Total Project | 11 months Team Salaries: £469,860 Additional Est.: AWS/Bedrock £30–50k + Tools £8k | Salaries only; cloud costs separate (tokens/compute). Cost control via Phase 2 reduction (~1/3).
Team and Cost Breakdown